## HOME
KTS PVT
VERSION NO: |  |  |  | VERIFIED BY:
TESTED BY: FATHIMA MUHAMMAD |  |  |  | DATE: 29/02/2024
ENVIRONMENT DETAILS: WINDOWS 11 MOZILLA FIREFOX |  |  |  | MODULE NAME : HOME
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
KTS _HM_01 | Check whether the page loads correctly | 1. Open kottakuzhiyil trades and servives page | www.ktspvt.com | The page should load correctly | The page loads correctly | PASS
KTS_HM_02 | Check whether the home link is clickable | 1. Open the page 2. Click on home |  | The home link should be clickable | The home link is clickable | PASS
KTS_HM_03 | Check whether the about link redirects to the desired page | 1. Open the page 2. Click on about |  | The about link should redirect to the desired page | The about link redirects to the desired page | PASS
KTS_HM_04 | Check whether the services page redirects to the service details | 1. Open the page 2. Click on services |  | The services link should redirect to the desired page | The services page redirects to the service details | PASS
KTS_HM_05 | Check whether the blogs link redirect to the blogs page itself | 1. Open the page 2. Click on blogs |  | The blogs link should redirect to the desired page | The blogs link redirect to the blogs page itself | PASS
KTS_HM_06 | Check whether the contact link redirect to the contact details of the website | 1. Open the page 2. Click on contact |  | The contact link should redirect to the desired page | The contact link redirect to the contact details of the website | PASS
KTS_HM_07 | Check whether all text are readable and understandable | 1. Open the page 2. Check all the text |  | All text should be readable and understandable | Some text are not readable and understandable | FAIL
KTS_HM_08 | Check whether the link is secured | 1. Open the page 2. Check the link |  | The link should be secured | The link is not secured | FAIL
KTS_HM_09 | Check whether the logo is present | 1. Open the page 2. Check for the logo |  | The logo should present | The logo is present | PASS
KTS_HM_10 | Check whether the enquire now link redirects to an enquiry form | 1. Open the page 2. Click on enquire now |  | The enquire now link should redirect to an enquiry form | The enquire now link redirects to an enquiry form | PASS
KTS_HM_11 | Check whether explore more link redirects into a page with more details | 1. Open the page 2. Click on explore more |  | Explore more link should redirect into a page with more details | Explore more link does not redirects into a page with more details | FAIL
KTS_HM_12 | Check whether read more about us link redirects into a page with more info | 1. Open the page 2. Click on read more |  | Read more about us link should redirect into a page with more info | Read more about us link does not redirect into a page with more info | FAIL
KTS_HM_13 | Check whether the read more link is clickable | 1. Open the page 2. Click on read more |  | The read more link should be clickable | The read more link is not clickable | FAIL
KTS_HM_14 | Check whether the photos of the CEO are provided | 1. Open the page 2. Click for the photos of CEOs |  | The photos of the CEO should be provided | The photos of the CEO are not provided | FAIL
KTS_HM_15 | Check whether the view all link under latest news and blogs redirects to the desired page | 1. Open the page 2. Check for the latest news and blogs session 3. Click view all |  | The view all link under latest news and blogs should redirect to the desired page | The view all link under latest news and blogs redirects to the desired page | FAIL
KTS_HM_16 | Check whether when clicked on phone number, it shows a pop-up | 1. Open the page 2. Click on the phone number |  | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | FAIL
KTS_HM_17 | Check whether the about kts under quick links is working | 1. Open the page 2. Click on about kts under quick links |  | The about kts under quick links should be working | The about kts under quick links is not working | FAIL
KTS_HM_18 | Check whether the services under quick links is working | 1. Open the page 2. Click on services under quick links |  | The services under quick links should be working | The services under quick links is not working | FAIL
KTS_HM_19 | Check whether the contact us under quick links is working | 1. Open the page 2. Click on contact under quick links |  | The contact us under quick links should be working | The contact under quick links is not working | FAIL
KTS_HM_20 | Check whether the blogs under quick links is working | 1. Open the page 2. Click on blogs under quick links |  | The contact us under quick links should be working | The blogs under quick links is not working | FAIL
KTS_HM_21 | Check whether social media links are present | 1. Open the page 2. Check for social media links |  | Social media links should be present | Social media links are not present | FAIL
KTS_HM_22 | Check whether all text boxes under get in touch field is editable | 1. Open the page 2. Check for get in touch session |  | All text boxes under get in touch field should be editable | All text boxes under get in touch field is editable | PASS
KTS_HM_23 | Check whether the name field does not accept characters other than alphabets in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter the name | Fathima123 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | FAIL
KTS_HM_24 | Check whether there is a limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter the name | Fathimaaaaaaaaaaaaaaaaaaaaaaa | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | FAIL
KTS_HM_25 | Check whether an email without domain name is not accepted in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter the email | Fathima2001 | An email without domain name should not be accepted in the get in touch | An email without domain name is not accepted in the get in touch | PASS
KTS_HM_26 | Check whether an invalid email is not accepted in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter an invalid email | abc@gmail.com | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | FAIL
KTS_HM_27 | Check whether there is a limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter the email | aaaaaaaaaaaaaaaabc@gmail.com | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | FAIL
KTS_HM_28 | Check whether an error is shown if an invalid email is entered in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter an invalid email | abc@gmail.com | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | FAIL
KTS_HM_29 | Check whether an error message is displayed if it does not contain domain name in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter an email without domain name | Fathima2001 | An error message should be displayed if it does not contain domain name in the get in touch | An error message is displayed if it does not contain domain name in the get in touch | PASS
KTS_HM_30 | Check whether the sent message button is working in the get in touch | 1. Open the page 2. Enter the details in get in touch 3. Click sent message |  | The sent message button should be working the get in touch | The sent message button is working in the get in touch | PASS
KTS_HM_31 | Check whether the fields that are required are marked as required the get in touch | 1. Open the page 2. Check for get in touch session 3. Check whether the required field is marked as required |  | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | FAIL
KTS_HM_32 | Check whether an error message is displayed if the required fields are not filled in the get in touch | 1. Open the page 2. Check for get in touch session 3. Check whether an error message is displayed if the required fields are not filled |  | An error message should be displayed if the required fields are not filled the get in touch | An error message is displayed if the required fields are not filled in the get in touch | PASS
KTS_HM_33 | Check whether the arrow mark at the bottom of the page when clicked take us to the top of the page | 1. Open the page 2. Scroll down to the bottom of the page 3. Click the arrow |  | The arrow mark at the bottom of the page when clicked should take us to the top of the page | The arrow mark at the bottom of the page when clicked take us to the top of the page | PASS
KTS_HM_34 | Check whether the design is done as per the SRS document | 1. Open the page 2. Check the design |  | The design should be done as per the SRS document | The design is done as per the SRS document | PASS
KTS_HM_35 | Check whether the super markets link redirects to the desired page | 1. Open the page 2. Click the super markets |  | The super markets link should redirect to the desired page | The super markets link redirect to the page which contain all services | FAIL
KTS_HM_36 | Check whether the car care link redirects to the desired page | 1. Open the page 2. Click the car care |  | The car care link should redirect to the desired page | The car care link redirect to the page which contain all services | FAIL
KTS_HM_37 | Check whether the truck spare parts link redirects to the desired page | 1. Open the page 2. Click the truck spare parts |  | The truck spare parts link should redirect to the desired page | The truck spare parts linK redirect to the page which contain all services | FAIL
KTS_HM_38 | Check whether the blogs links redirect to the corresponding heading blog itself | 1. Open the page 2. Click a specific topic from blog |  | The blogs links should redirect to the corresponding heading blog itself | The blogs links redirect to the corresponding heading blog itself | PASS
KTS_HM_39 | Check whether the published date is present on the image of the blog | 1. Open the page 2. Check the date of publishing of blog on the image by keeping the mouse pointer on it |  | The published date should be present on the image of the blog | The published date is present on the image of the blog | PASS
KTS_HM_40 | Check whether all text boxes of enquiry form are editable | 1. Open the page 2. Click on enquire now |  | All text boxes of enquiry form should be editable | All text boxes of enquiry form are editable | PASS
KTS_HM_41 | Check whether the name field of enquiry form does not accept characters other than alphabets | 1. Open the page 2. Click on enquire now 3. Enter the name | Fathima | The name field of enquiry form should not accept characters other than alphabets | The name field of enquiry form accept characters other than alphabets | FAIL
KTS_HM_42 | Check whether there is a limit for the number of characters in the name field in enquiry form | 1. Open the page 2. Click on enquire now 3. Enter the name | Fathimaaaaaaaaaaaaaaaaaaaaaaa | There should be a limit for the number of characters in the name field in enquiry form | There is no limit for the number of characters in the name field in enquiry form | FAIL
KTS_HM_43 | Check whether an email without domain name is not accepted in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter an email without domain name | Fathima2001 | An email without domain name should not be accepted in the enquiry form | An email without domain name is not accepted in the enquiry form | PASS
KTS_HM_44 | Check whether an invalid email is not accepted in enquiry form | 1. Open the page 2. Click on enquire now 3. Enter an invalid email | abc@gmail.com | An invalid email should not be accepted in enquiry form | An invalid email is accepted in enquiry form | FAIL
KTS_HM_45 | Check whether there is a limit for the number of characters in the email field in enquiry form | 1. Open the page 2. Click on enquire now 3. Enter an email | aaaaaaaaaaaaaaaabc@gmail.com | There should be a limit for the number of characters in the email field in enquiry form | There is no limit for the number of characters in the email field in enquiry form | FAIL
KTS_HM_46 | Check whether an error is shown if an invalid email is entered in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter an invalid email | abc@gmail.com | An error should be shown if an invalid email is entered in the enquiry form | An error is not shown if an invalid email is entered in the enquiry form | FAIL
KTS_HM_47 | Check whether an error message is displayed if it does not contain domain name | 1. Open the page 2. Click on enquire now 3. Enter an email without domain name | Fathima2001 | An error message should be displayed if it does not contain domain name | an error message is displayed if it does not contain domain name | PASS
KTS_HM_48 | Check whether the submit button is working in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter the details 4. Click submit | Fathima Fathima123@gmail.com 1234567890 Super markets | The submit button should be working in the enquiry form | The submit button is working in the enquiry form | PASS
KTS_HM_49 | Check whether the fields that are required are marked as required in enquiry form | 1. Open the page 2. Click on enquire now 3. Check whether the required field is marked as required |  | The fields that are required should be marked as required in enquiry form | The fields that are required are not marked as required in enquiry form | PASS
KTS_HM_50 | Check whether an error message is displayed if the required fields are not filled in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter details by leaving a required field |  | An error message should be displayed if the required fields are not filled in the enquiry form | An error message is displayed if the required fields are not filled in the enquiry form | PASS
KTS_HM_51 | Check whether the number field does not accept alphabets in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter the number | 123456abcde | The number field should not accept alphabets in the enquiry form | The number field accept alphabets in the enquiry form | FAIL
KTS_HM_52 | Check whether there is a limit of number of digits that can be entered in the number field | 1. Open the page 2. Click on enquire now 3. Enter the number | 11111111111 | There should be a limit of number of digits that can be entered in the number field | There is no limit of number of digits that can be entered in the number field | FAIL
KTS_HM_53 | Check whether the name field does not accept space as a text in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter a space in name field 4. Click submit |  | The name field should not accept space as a text in the enquiry form | The field not accept space as a text in the enquiry form | FAIL
KTS_HM_54 | Check whether the number field does not accept space as a text in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter a space in number field 4. Click submit |  | The number field should not accept space as a text in the enquiry form | The number field accept space as a text in the enquiry form | FAIL
KTS_HM_55 | Check whether the service field does not accept space as a text in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter a space in service field 4. Click submit |  | The service field should not accept space as a text in the enquiry form | The service field accept space as a text in the enquiry form | FAIL
KTS_HM_56 | Check whether a message sent message is displayed if it is sent in enquiry form | 1. Open the page 2. Click on enquire now 3. Enter details 4. Click submit 5. Check for a message showing message have been sent | Fathima Fathima123@gmail.com 1234567890 Super markets | A message sent message should be displayed if it is sent in enquiry form | A message sent message is displayed if it is sent in enquiry form | PASS
KTS_HM_57 | Check whether a message sent message is displayed if it is sent in get in touch form | 1. Open the page 2. Go to get in touch session 3. Enter details 4. Click send message 5. Check for a message showing message have been sent | Fathima Fathima123@gmail.com Super markets Very good service | A message sent message should be displayed if it is sent in get in touch form | A message sent message is displayed if it is sent in get in touch form | PASS
KTS_HM_58 | Check whether the number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on enquire now 3. Enter the number | 1234567890 | The number field should accept number within the given format as per the SRS document | The number field accept number other than the given format as per the SRS document | FAIL
KTS_HM_59 | Check whether the color standards are as per the SRS document | 1. Open the page 2. Check the color standards |  | The color standards should be as per the SRS document | The color standards are as per the SRS document | PASS
KTS_HM_60 | Check whether the fonts and texts are as per the SRS document | 1. Open the page 2. Check the text and fonts |  | The fonts and texts should be as per the SRS document | The fonts and texts are as per the SRS document | PASS
KTS_HM_61 | Check whether the name field does not accept space as a text in the get in touch form | 1. Open the page 2. Go to get in touch 3. Enter a space in name field 4. Click send message |  | The name field should not accept space as a text in the get in touch form | The field not accept space as a text in the get in touch form | FAIL
KTS_HM_62 | Check whether the subject field does not accept space as a text in the get in touch form | 1. Open the page 2. Go to get in touch 3. Enter a space in subject field 4. Click send message |  | The subject field should not accept space as a text in the get in touch form | The subject field accept space as a text in the get in touch form | FAIL
KTS_HM_63 | Check whether the message field does not accept space as a text in the get in touch form | 1. Open the page 2. Go to get in touch 3. Enter a space in message field 4. Click send message |  | The message field should not accept space as a text in the get in touch form | The message field accept space as a text in the get in touch form | FAIL
KTS_HM_64 | Check whether when clicked on the logo, it redirects to the home page | 1. Open the page 2. Click on the logo |  | When clicked on the logo, it should redirect to the home page | When clicked on the logo, it redirects to the home page | PASS
KTS_HM_65 | Check whether the logo is present in the position specified in the SRS document | 1. Open the page 2. Check the logo position |  | The logo should be present in the position specified in the SRS document | The logo is present in the position specified in the SRS document | PASS

## ABOUT
KTS PVT
VERSION NO: |  |  |  | VERIFIED BY:
TESTED BY: FATHIMA MUHAMMAD |  |  |  | DATE: 29/02/2024
ENVIRONMENT DETAILS: WINDOWS 11 MOZILLA FIREFOX |  |  |  | MODULE NAME : ABOUT
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
KTS_ABT_01 | Check whether the about page loads properly when clicked on about | 1. Open the page 2. Click on about | www.ktspvt.com | The about page should load properly when clicked on about | The about page loads properly when clicked on about | PASS
KTS_ABT_02 | Check whether the color standards are as per the SRS document | 1. Open the page 2. Click on about 3. Check the color standards |  | The color standards should be as per the SRS document | The color standards are as per the SRS document | PASS
KTS_ABT_03 | Check whether the text are readable and understandable | 1. Open the page 2. Click on about |  | The text should be readable and understandable | The text is readable and understandable | PASS
KTS_ABT_04 | Check whether when clicked on phone number, it shows a pop-up | 1. Open the page 2. Click on about 3. Click on the phone number |  | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | FAIL
KTS_ABT_05 | Check whether the about kts under quick links is working | 1. Open the page 2. Click on about 3. Click on about kts under quick links |  | The about kts under quick links should be working | The about kts under quick links is not working | FAIL
KTS_ABT_06 | Check whether the services under quick links is working | 1. Open the page 2. Click on about 3. Click on services under quick links |  | The services under quick links should be working | The services under quick links is not working | FAIL
KTS_ABT_07 | Check whether the contact us under quick links is working | 1. Open the page 2. Click on about 3. Click on contact under quick links |  | The contact us under quick links should be working | The contact under quick links is not working | FAIL
KTS_ABT_08 | Check whether the blogs under quick links is working | 1. Open the page 2. Click on about 3. Click on blogs under quick links |  | The blogs us under quick links should be working | The blogs under quick links is not working | FAIL
KTS_ABT_09 | Check whether all text boxes under get in touch field is editable | 1. Open the page 2. Click on about 3. Check for get in touch session |  | All text boxes under get in touch field should be editable | All text boxes under get in touch field is editable | PASS
KTS_ABT_10 | Check whether the name field does not accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter the name | Fathima123 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | FAIL
KTS_ABT_11 | Check whether there is a limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter the name | Fathimaaaaaaaaaaaaaaaaaaaaaaa | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | FAIL
KTS_ABT_12 | Check whether an email without domain name is not accepted in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter the email | Fathima2001 | An email without domain name should not be accepted in the get in touch | An email without domain name is not accepted in the get in touch | PASS
KTS_ABT_13 | Check whether an invalid email is not accepted in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | FAIL
KTS_ABT_14 | Check whether there is a limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter the email | aaaaaaaaaaaaaaaabc@gmail.com | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | FAIL
KTS_ABT_15 | Check whether an error is shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | FAIL
KTS_ABT_16 | Check whether an error message is displayed if it does not contain domain name in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter an email without domain name | Fathima2001 | An error message should be displayed if it does not contain domain name in the get in touch | An error message is displayed if it does not contain domain name in the get in touch | PASS
KTS_ABT_17 | Check whether the sent message button is working in the get in touch | 1. Open the page 2. Click on about 3. Enter the details in get in touch 4. Click sent message |  | The sent message button should be working the get in touch | The sent message button is working in the get in touch | PASS
KTS_ABT_18 | Check whether the fields that are required are marked as required the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Check whether the required field is marked as required |  | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | FAIL
KTS_ABT_19 | Check whether an error message is displayed if the required fields are not filled in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Check whether an error message is displayed if the required fields are not filled |  | An error message should be displayed if the required fields are not filled the get in touch | An error message is displayed if the required fields are not filled in the get in touch | PASS
KTS_ABT_20 | Check whether the arrow mark at the bottom of the page when clicked take us to the top of the page | 1. Open the page 2. Click on about 3. Scroll down to the bottom of the page 4. Click the arrow |  | The arrow mark at the bottom of the page when clicked should take us to the top of the page | The arrow mark at the bottom of the page when clicked take us to the top of the page | PASS
KTS_ABT_21 | Check whether the design is done as per the SRS document | 1. Open the page 2. Click on about 3. Check the design |  | The design should be done as per the SRS document | The design is done as per the SRS document | PASS
KTS_ABT_22 | Check whether a message sent message is displayed if it is sent in get in touch form | 1. Open the page 2. Click on about 3. Go to get in touch session 4. Enter details 5. Click send message 6. Check for a message showing message have been sent | Fathima Fathima123@gmail.com Super markets Very good service | A message sent message should be displayed if it is sent in get in touch form | A message sent message is displayed if it is sent in get in touch form | PASS
KTS_ABT_23 | Check whether the number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on about 3. Click on enquire now 4. Enter the number | 1234567890 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | FAIL
KTS_ABT_24 | Check whether the name field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on about 3. Go to get in touch 4. Enter a space in name field 5. Click send message |  | The name field should not accept space as a text in the enquiry form | The field not accept space as a text in the enquiry form | FAIL
KTS_ABT_25 | Check whether the subject field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on about 3. Go to get in touch 4. Enter a space in subject field 5. Click send message |  | The subject field should not accept space as a text in the enquiry form | The subject field accept space as a text in the enquiry form | FAIL
KTS_ABT_26 | Check whether the message field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on about 3. Go to get in touch 4. Enter a space in message field 5. Click send message |  | The message field should not accept space as a text in the enquiry form | The message field accept space as a text in the enquiry form | FAIL
KTS_ABT_27 | Check whether the fonts and texts are as per the SRS document | 1. Open the page 2. Click on about 3. Check the text and fonts |  | The fonts and texts should be as per the SRS document | The fonts and texts are as per the SRS document | PASS

## SERVICES
KTS PVT
VERSION NO: |  |  |  | VERIFIED BY:
TESTED BY: FATHIMA MUHAMMAD |  |  |  | DATE: 29/02/2024
ENVIRONMENT DETAILS: WINDOWS 11 MOZILLA FIREFOX |  |  |  | MODULE NAME : SERVICES
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
KTS_SRV_01 | Check whether the services page loads properly when clicked on about | 1. Open the page 2. Click on services | www.ktspvt.com | The services page should load properly when clicked on about | The services page loads properly when clicked on about | PASS
KTS_SRV_02 | Check whether the color standards are as per the SRS document | 1. Open the page 2. Click on services 3. Check the color standards |  | The color standards should be as per the SRS document | The color standards are as per the SRS document | PASS
KTS_SRV_03 | Check whether the text are readable and understandable | 1. Open the page 2. Click on services |  | The text should be readable and understandable | The text is readable and understandable | PASS
KTS_SRV_04 | Check whether when clicked on phone number, it shows a pop-up | 1. Open the page 2. Click on services 3. Click on the phone number |  | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | FAIL
KTS_SRV_05 | Check whether the about kts under quick links is working | 1. Open the page 2. Click on services 3. Click on about kts under quick links |  | The about kts under quick links should be working | The about kts under quick links is not working | FAIL
KTS_SRV_06 | Check whether the services under quick links is working | 1. Open the page 2. Click on services 3. Click on services under quick links |  | The services under quick links should be working | The services under quick links is not working | FAIL
KTS_SRV_07 | Check whether the contact us under quick links is working | 1. Open the page 2. Click on services 3. Click on contact under quick links |  | The contact us under quick links should be working | The contact us under quick links is not working | FAIL
KTS_SRV_08 | Check whether the blogs under quick links is working | 1. Open the page 2. Click on services 3. Click on blogs under quick links |  | The blogs under quick links should be working | The blogs under quick links is not working | FAIL
KTS_SRV_09 | Check whether all text boxes under get in touch field is editable | 1. Open the page 2. Click on services 3. Check for get in touch session |  | All text boxes under get in touch field should be editable | All text boxes under get in touch field is editable | PASS
KTS_SRV_10 | Check whether the name field does not accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter the name | Fathima123 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | FAIL
KTS_SRV_11 | Check whether there is a limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter the name | Fathimaaaaaaaaaaaaaaaaaaaaaaa | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | FAIL
KTS_SRV_12 | Check whether an email without domain name is not accepted in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter the email | Fathima2001 | An email without domain name should not be accepted in the get in touch | An email without domain name is not accepted in the get in touch | PASS
KTS_SRV_13 | Check whether an invalid email is not accepted in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | FAIL
KTS_SRV_14 | Check whether there is a limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter the email | aaaaaaaaaaaaaaaabc@gmail.com | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | FAIL
KTS_SRV_15 | Check whether an error is shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | FAIL
KTS_SRV_16 | Check whether an error message is displayed if it does not contain domain name in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter an email without domain name | Fathima2001 | An error message should be displayed if it does not contain domain name in the get in touch | An error message is displayed if it does not contain domain name in the get in touch | PASS
KTS_SRV_17 | Check whether the sent message button is working in the get in touch | 1. Open the page 2. Click on services 3. Enter the details in get in touch 4. Click sent message |  | The sent message button should be working the get in touch | The sent message button is working in the get in touch | PASS
KTS_SRV_18 | Check whether the fields that are required are marked as required the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Check whether the required field is marked as required |  | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | FAIL
KTS_SRV_19 | Check whether an error message is displayed if the required fields are not filled in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Check whether an error message is displayed if the required fields are not filled |  | An error message should be displayed if the required fields are not filled the get in touch | An error message is displayed if the required fields are not filled in the get in touch | PASS
KTS_SRV_20 | Check whether the arrow mark at the bottom of the page when clicked take us to the top of the page | 1. Open the page 2. Click on services 3. Scroll down to the bottom of the page 4. Click the arrow |  | The arrow mark at the bottom of the page when clicked should take us to the top of the page | The arrow mark at the bottom of the page when clicked take us to the top of the page | PASS
KTS_SRV_21 | Check whether the design is done as per the SRS document | 1. Open the page 2. Click on services 3. Check the design |  | The design should be done as per the SRS document | The design is done as per the SRS document | PASS
KTS_SRV_22 | Check whether a message sent message is displayed if it is sent in get in touch form | 1. Open the page 2. Click on services 3. Go to get in touch session 4. Enter details 5. Click send message 6. Check for a message showing message have been sent | Fathima Fathima123@gmail.com Super markets Very good service | A message sent message should be displayed if it is sent in get in touch form | A message sent message is displayed if it is sent in get in touch form | PASS
KTS_SRV_23 | Check whether the number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on services 3. Click on enquire now 4. Enter the number | 1234567890 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | FAIL
KTS_SRV_24 | Check whether the name field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on services 3. Go to get in touch 4. Enter a space in name field 5. Click send message |  | The name field should not accept space as a text in the enquiry form | The field not accept space as a text in the enquiry form | FAIL
KTS_SRV_25 | Check whether the subject field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on services 3. Go to get in touch 4. Enter a space in subject field 5. Click send message |  | The subject field should not accept space as a text in the enquiry form | The subject field accept space as a text in the enquiry form | FAIL
KTS_SRV_26 | Check whether the message field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on services 3. Go to get in touch 4. Enter a space in message field 5. Click send message |  | The message field should not accept space as a text in the enquiry form | The message field accept space as a text in the enquiry form | FAIL
KTS_SRV_27 | Check whether the fonts and texts are as per the SRS document | 1. Open the page 2. Click on services 3. Check the text and fonts |  | The fonts and texts should be as per the SRS document | The fonts and texts are as per the SRS document | PASS
KTS_SRV_28 | Check whether we can open the images | 1. Open the page 2. Click on services 3. Click on an image |  | We should be able to open the images | We can open the images | PASS
KTS_SRV_29 | Check whether the images gets swipped automatically | 1. Open the page 2. Click on services |  | The images should get swipped automatically | The images gets swipped automatically | PASS
KTS_SRV_30 | Check whether there is a next arrow to show next images | 1. Open the page 2. Click on services 3. Click on next arrow near image |  | There should be a next arrow to show next images | There is a next arrow to show next images | PASS
KTS_SRV_31 | Check whether the allignment of image is as per the SRS document | 1. Open the page 2. Click on services 3. Check the images |  | The allignment of image should be as per the SRS document | The allignment of image is as per the SRS document | PASS
KTS_SRV_32 | Check whether there is a back arrow to show previous images | 1. Open the page 2. Click on services 3. Click on back arrow near image |  | There should be a back arrow to show previous images | There is a back arrow to show previous images | PASS
KTS_SRV_33 | Check whether we can zoom in each image | 1. Open the page 2. Click on services 3. Open an image 4. Zoom in using the + botton |  | We should be able to zoom in each image | We can zoom in each image | PASS
KTS_SRV_34 | Check whether we can zoom out each image | 1. Open the page 2. Click on services 3. Open an image 4. Zoom in using the - botton |  | We should be able to zoom out each image | We can zoom out each image | PASS
KTS_SRV_35 | Check whether the image is displayed in order itself | 1. Open the page 2. Click on services 3. Check the images |  | The image should be displayed in order itself | The image is displayed in order itself | PASS
KTS_SRV_36 | Check whether the number of image being displayed is showed at the top | 1. Open the page 2. Click on services 3. Open an image 4. Check the number of image |  | The number of image being displayed should be showed at the top | The number of image being displayed is showed at the top | PASS
KTS_SRV_37 | Check whether there is a close botton at the top to close an image | 1. Open the page 2. Click on services 3. Open an image 4. Click on x to close it |  | There should be a close botton at the top to close an image | There is a close botton at the top to close an image | PASS
KTS_SRV_38 | Check whether the image shown is of the corresponding heading itself | 1. Open the page 2. Click on services 3. Check the images |  | The image shown should be of the corresponding heading itself | The image shown is of the corresponding heading itself | PASS
KTS_SRV_39 | Check whether it does not take too long to load the image while opened | 1. Open the page 2. Click on services 3. Open an image |  | It should not take too long to load the image while opened | It does not take too long to load the image while opened | PASS
KTS_SRV_40 | Check whether all services available are provided in the services page as per the SRS document | 1. Open the page 2. Click on services 3. Check the services |  | All services available should be provided in the services page as per the SRS document | All services available are provided in the services page as per the SRS document | PASS

## BLOGS
KTS PVT
VERSION NO: |  |  |  | VERIFIED BY:
TESTED BY: FATHIMA MUHAMMAD |  |  |  | DATE: 29/02/2024
ENVIRONMENT DETAILS: WINDOWS 11 MOZILLA FIREFOX |  |  |  | MODULE NAME : BLOGS
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
KTS_BLG_01 | Check whether the blogs page loads properly when clicked on about | 1. Open the page 2. Click on blogs | www.ktspvt.com | The blogs page should load properly when clicked on about | The blogs page loads properly when clicked on about | PASS
KTS_BLG_02 | Check whether the color standards are as per the SRS document | 1. Open the page 2. Click on blogs 3. Check the color standards |  | The color standards should be as per the SRS document | The color standards are as per the SRS document | PASS
KTS_BLG_03 | Check whether the text are readable and understandable | 1. Open the page 2. Click on blogs |  | The text should be readable and understandable | The text is not readable and understandable | FAIL
KTS_BLG_04 | Check whether when clicked on phone number, it shows a pop-up | 1. Open the page 2. Click on blogs 3. Click on the phone number |  | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | FAIL
KTS_BLG_05 | Check whether the about kts under quick links is working | 1. Open the page 2. Click on blogs 3. Click on about kts under quick links |  | The about kts under quick links should be working | The about kts under quick links is not working | FAIL
KTS_BLG_06 | Check whether the services under quick links is working | 1. Open the page 2. Click on blogs 3. Click on services under quick links |  | The services under quick links should be working | The services under quick links is not working | FAIL
KTS_BLG_07 | Check whether the contact us under quick links is working | 1. Open the page 2. Click on blogs 3. Click on contact under quick links |  | The contact us under quick links should be working | The contact under quick links is not working | FAIL
KTS_BLG_08 | Check whether the blogs under quick links is working | 1. Open the page 2. Click on blogs 3. Click on blogs under quick links |  | The blogs under quick links should be working | The blogs under quick links is not working | FAIL
KTS_BLG_09 | Check whether all text boxes under get in touch field is editable | 1. Open the page 2. Click on blogs 3. Check for get in touch session |  | All text boxes under get in touch field should be editable | All text boxes under get in touch field is editable | PASS
KTS_BLG_10 | Check whether the name field does not accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the name | Fathima123 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | FAIL
KTS_BLG_11 | Check whether there is a limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the name | Fathimaaaaaaaaaaaaaaaaaaaaaaa | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | FAIL
KTS_BLG_12 | Check whether an email without domain name is not accepted in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the email | Fathima2001 | An email without domain name should not be accepted in the get in touch | An email without domain name is not accepted in the get in touch | PASS
KTS_BLG_13 | Check whether an invalid email is not accepted in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | FAIL
KTS_BLG_14 | Check whether there is a limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the email | aaaaaaaaaaaaaaaabc@gmail.com | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | FAIL
KTS_BLG_15 | Check whether an error is shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | FAIL
KTS_BLG_16 | Check whether an error message is displayed if it does not contain domain name in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter an email without domain name | Fathima2001 | An error message should be displayed if it does not contain domain name in the get in touch | An error message is displayed if it does not contain domain name in the get in touch | PASS
KTS_BLG_17 | Check whether the sent message button is working in the get in touch | 1. Open the page 2. Click on blogs 3. Enter the details in get in touch 4. Click sent message |  | The sent message button should be working the get in touch | The sent message button is working in the get in touch | PASS
KTS_BLG_18 | Check whether the fields that are required are marked as required the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Check whether the required field is marked as required |  | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | FAIL
KTS_BLG_19 | Check whether an error message is displayed if the required fields are not filled in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Check whether an error message is displayed if the required fields are not filled |  | An error message should be displayed if the required fields are not filled the get in touch | An error message is displayed if the required fields are not filled in the get in touch | PASS
KTS_BLG_20 | Check whether the arrow mark at the bottom of the page when clicked take us to the top of the page | 1. Open the page 2. Click on blogs 3. Scroll down to the bottom of the page 4. Click the arrow |  | The arrow mark at the bottom of the page when clicked should take us to the top of the page | The arrow mark at the bottom of the page when clicked take us to the top of the page | PASS
KTS_BLG_21 | Check whether the design is done as per the SRS document | 1. Open the page 2. Click on blogs 3. Check the design |  | The design should be done as per the SRS document | The design is done as per the SRS document | PASS
KTS_BLG_22 | Check whether a message sent message is displayed if it is sent in get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch session 4. Enter details 5. Click send message 6. Check for a message showing message have been sent | Fathima Fathima123@gmail.com Super markets Very good service | A message sent message should be displayed if it is sent in get in touch form | A message sent message is displayed if it is sent in get in touch form | PASS
KTS_BLG_23 | Check whether the number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on blogs 3. Click on enquire now 4. Enter the number | 1234567890 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | FAIL
KTS_BLG_24 | Check whether the name field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in name field 5. Click send message |  | The name field should not accept space as a text in the enquiry form | The field not accept space as a text in the enquiry form | FAIL
KTS_BLG_25 | Check whether the subject field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in subject field 5. Click send message |  | The subject field should not accept space as a text in the enquiry form | The subject field accept space as a text in the enquiry form | FAIL
KTS_BLG_26 | Check whether the message field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in message field 5. Click send message |  | The message field should not accept space as a text in the enquiry form | The message field accept space as a text in the enquiry form | FAIL
KTS_BLG_27 | Check whether the fonts and texts are as per the SRS document | 1. Open the page 2. Click on blogs 3. Check the text and fonts |  | The fonts and texts should be as per the SRS document | The fonts and texts are as per the SRS document | PASS
KTS_BLG_28 | Check whether the correspodning blog itself is opened when clicked | 1. Open the page 2. Click on blogs 3. Click on a blog |  | The correspodning blog itself should be opened when clicked | The correspodning blog itself is opened when clicked | PASS
KTS_BLG_29 | Check whether a message is shown if comment is disabled | 1. Open the page 2. Click on blogs 3. Click on a blog 4. Check whether the comment session is disabled |  | A message should be shown if comment is disabled | A message is shown if comment is disabled | PASS
KTS_BLG_30 | Check whether there is a comment session | 1. Open the page 2. Click on blogs 3. Click on a blog 4. Check for the comment session |  | There should be a comment session | There is a comment session | PASS

## CONTACT
KTS PVT
VERSION NO: |  |  |  | VERIFIED BY:
TESTED BY: FATHIMA MUHAMMAD |  |  |  | DATE: 29/02/2024
ENVIRONMENT DETAILS: WINDOWS 11 MOZILLA FIREFOX |  |  |  | MODULE NAME : CONTACT
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
KTS_CNT_01 | Check whether the contact page loads properly when clicked on about | 1. Open the page 2. Click on contact | www.ktspvt.com | The contact page should load properly when clicked on about | The contact page loads properly when clicked on about | PASS
KTS_CNT_02 | Check whether the color standards are as per the SRS document | 1. Open the page 2. Click on contact 3. Check the color standards |  | The color standards should be as per the SRS document | The color standards are as per the SRS document | PASS
KTS_CNT_03 | Check whether the text are readable and understandable | 1. Open the page 2. Click on contact |  | The text should be readable and understandable | The text is not readable and understandable | FAIL
KTS_CNT_04 | Check whether when clicked on phone number, it shows a pop-up | 1. Open the page 2. Click on contact 3. Click on the phone number |  | When clicked on phone number, it should show a pop-up | When clicked on phone number, it show a pop-up | PASS
KTS_CNT_05 | Check whether the about kts under quick links is working | 1. Open the page 2. Click on contact 3. Click on about kts under quick links |  | The about kts under quick links should be working | The about kts under quick links is not working | FAIL
KTS_CNT_06 | Check whether the services under quick links is working | 1. Open the page 2. Click on contact 3. Click on services under quick links |  | The services under quick links should be working | The services under quick links is not working | FAIL
KTS_CNT_07 | Check whether the contact us under quick links is working | 1. Open the page 2. Click on contact 3. Click on contact under quick links |  | The contact us under quick links should be working | The contact under quick links is not working | FAIL
KTS_CNT_08 | Check whether the blogs under quick links is working | 1. Open the page 2. Click on contact 3. Click on blogs under quick links |  | The blogs under quick links should be working | The blogs under quick links is not working | FAIL
KTS_CNT_09 | Check whether all text boxes under get in touch field is editable | 1. Open the page 2. Click on contact 3. Check for get in touch session |  | All text boxes under get in touch field should be editable | All text boxes under get in touch field is editable | PASS
KTS_CNT_10 | Check whether the name field does not accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Enter the name | Fathima123 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | FAIL
KTS_CNT_11 | Check whether there is a limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Enter the name | Fathimaaaaaaaaaaaaaaaaaaaaaaa | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | FAIL
KTS_CNT_12 | Check whether an email without domain name is not accepted in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Enter the email | Fathima2001 | An email without domain name should not be accepted in the get in touch | An email without domain name is not accepted in the get in touch | PASS
KTS_CNT_13 | Check whether an invalid email is not accepted in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | FAIL
KTS_CNT_14 | Check whether there is a limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Enter the email | aaaaaaaaaaaaaaaabc@gmail.com | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | FAIL
KTS_CNT_15 | Check whether an error is shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Enter an invalid email | abc@gmail.com | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | FAIL
KTS_CNT_16 | Check whether an error message is displayed if it does not contain domain name in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Enter an email without domain name | Fathima2001 | An error message should be displayed if it does not contain domain name in the get in touch | An error message is displayed if it does not contain domain name in the get in touch | PASS
KTS_CNT_17 | Check whether the sent message button is working in the get in touch | 1. Open the page 2. Click on contact 3. Enter the details in get in touch 4. Click sent message |  | The sent message button should be working the get in touch | The sent message button is working in the get in touch | PASS
KTS_CNT_18 | Check whether the fields that are required are marked as required the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Check whether the required field is marked as required |  | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | FAIL
KTS_CNT_19 | Check whether an error message is displayed if the required fields are not filled in the get in touch | 1. Open the page 2. Click on contact 3. Check for get in touch session 4. Check whether an error message is displayed if the required fields are not filled |  | An error message should be displayed if the required fields are not filled the get in touch | An error message is displayed if the required fields are not filled in the get in touch | PASS
KTS_CNT_20 | Check whether the arrow mark at the bottom of the page when clicked take us to the top of the page | 1. Open the page 2. Click on contact 3. Scroll down to the bottom of the page 4. Click the arrow |  | The arrow mark at the bottom of the page when clicked should take us to the top of the page | The arrow mark at the bottom of the page when clicked take us to the top of the page | PASS
KTS_CNT_21 | Check whether the design is done as per the SRS document | 1. Open the page 2. Click on contact 3. Check the design |  | The design should be done as per the SRS document | The design is done as per the SRS document | PASS
KTS_CNT_22 | Check whether a message sent message is displayed if it is sent in get in touch form | 1. Open the page 2. Click on contact 3. Go to get in touch session 4. Enter details 5. Click send message 6. Check for a message showing message have been sent | Fathima Fathima123@gmail.com Super markets Very good service | A message sent message should be displayed if it is sent in get in touch form | A message sent message is displayed if it is sent in get in touch form | PASS
KTS_CNT_23 | Check whether the number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on contact 3. Click on enquire now 4. Enter the number | 1234567890 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | FAIL
KTS_CNT_24 | Check whether the name field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on contact 3. Go to get in touch 4. Enter a space in name field 5. Click send message |  | The name field should not accept space as a text in the enquiry form | The field not accept space as a text in the enquiry form | FAIL
KTS_CNT_25 | Check whether the subject field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in subject field 5. Click send message |  | The subject field should not accept space as a text in the enquiry form | The subject field accept space as a text in the enquiry form | FAIL
KTS_CNT_26 | Check whether the message field does not accept space as a text in the get in touch form | 1. Open the page 2. Click on contact 3. Go to get in touch 4. Enter a space in message field 5. Click send message |  | The message field should not accept space as a text in the enquiry form | The message field accept space as a text in the enquiry form | FAIL
KTS_CNT_27 | Check whether the fonts and texts are as per the SRS document | 1. Open the page 2. Click on contact 3. Check the text and fonts |  | The fonts and texts should be as per the SRS document | The fonts and texts are as per the SRS document | PASS
KTS_CNT_28 | Check whether it is redirected to mail when clicked on the email id | 1. Open the page 2. Click on contact 3. Click on email |  | It should be redirected to mail when clicked on the email id | It is redirected to mail when clicked on the email id | PASS
KTS_CNT_29 | Check whether it is redirected to the corresponding address map when clicked on address | 1. Open the page 2. Click on contact 3. Click on address |  | It should be redirected to the corresponding address map when clicked on address | It is redirected to the corresponding address map when clicked on address | PASS
KTS_CNT_30 | Check whether there is a google map location present in the page | 1. Open the page 2. Click on contact 3. Check for the map location |  | There should be a google map location present in the page | There is a google map location present in the page | PASS
KTS_CNT_31 | Check whether the key shortcuts are displayed when clicked on keyboard shortcuts | 1. Open the page 2. Click on contact 3. Click on keyboard shortcuts |  | The key shortcuts should be displayed when clicked on keyboard shortcuts | The key shortcuts are displayed when clicked on keyboard shortcuts | PASS
KTS_CNT_32 | Check whether it is able to view the map larger by clicking view larger map | 1. Open the page 2. Click on contact 3. Click on view larger map |  | It should be able to view the map larger by clicking view larger map | It is able to view the map larger by clicking view larger map | PASS
KTS_CNT_33 | Check whether it is redirecting to the reviews page when clicked on reviews | 1. Open the page 2. Click on contact 3. Click on reviews |  | It should be redirected to the reviews page when clicked on reviews | It is redirecting to the reviews page when clicked on reviews | PASS
KTS_CNT_34 | Check whether it is provided with directions to reach the location when clicked on directions | 1. Open the page 2. Click on contact 3. Click on directions |  | It should be provided with directions to reach the location when clicked on directions | It is provided with directions to reach the location when clicked on directions | PASS
KTS_CNT_35 | Check whether it is redirected to the terms of map when clicked on terms | 1. Open the page 2. Click on contact 3. Click on terms |  | It should be redirected to the terms of map when clicked on terms | It is redirected to the terms of map when clicked on terms | PASS
KTS_CNT_36 | Check whether it is able to report a map error by clicking the report a map error link | 1. Open the page 2. Click on contact 3. Click on report a map error |  | It should be able to report a map error by clicking the report a map error link | It is able to report a map error by clicking the report a map error link | PASS
KTS_CNT_37 | Check whether it is able to zoom in using the + symbol | 1. Open the page 2. Click on contact 3. Click on + |  | It should be able to zoom in using the + symbol | It is able to zoom in using the + symbol | PASS
KTS_CNT_38 | Check whether it is able to zoom out using the - symbol | 1. Open the page 2. Click on contact 3. Click on - |  | It should be able to zoom out using the - symbol | It is able to zoom out using the - symbol | PASS
KTS_CNT_39 | Check whether satellite images are displayed when clicked on show satellite imagery | 1. Open the page 2. Click on contact 3. Click on show satellite imagery |  | Satellite images should be displayed when clicked on show satellite imagery | Satellite images are displayed when clicked on show satellite imagery | PASS
KTS_CNT_40 | Check whether the given location is correct | 1. Open the page 2. Click on contact 3. Click on the map |  | The given location should be correct | The given location is not correct | FAIL
KTS_CNT_41 | Check whether it is able to drag the map using the mouse pointer | 1. Open the page 2. Click on contact 3. Drag the map using mouse |  | It should be able to drag the map using the mouse pointer | It is able to drag the map using the mouse pointer | PASS
KTS_CNT_42 | Check whether it is able to zoom in and out by pressing control botton and scrolling | 1. Open the page 2. Click on contact 3. Press control botton and scroll mouse |  | It should be able to zoom in and out by pressing control botton and scrolling | It is able to zoom in and out by pressing control botton and scrolling | PASS
KTS_CNT_43 | Check whether the given number is valid | 1. Open the page 2. Click on contact 3. Check the number |  | The given number should be valid | The given number is valid | PASS
KTS_CNT_44 | Check whether the email is valid | 1. Open the page 2. Click on contact 3. Check the email |  | The given email should be valid | The email is valid | PASS
KTS_CNT_45 | Check whether the page does not take too long to load | 1. Open the page 2. Click on contact |  | The page should not take too long to load | The page does not take too long to load | PASS

## BUG REPORT
BUG REPORT
Identified by :- Fathima Muhammad
Reported to :- Rugma
Date :- 29/02/2024
Environment Details :- WINDOWS 10 MOZILLA FIREFOX
Bug ID | Test ID | Expected Result | Bug Summary | Stepstoreproduce | Severity | Priority | Screenshot | Status
DEF_KTS_HM_01 | KTS_HM_07 | All text should be readable and understandable | Some text are not readable and understandable | 1. Open the page 2. Check all the text | Trivial |  | https://drive.google.com/file/d/1BgZG65dIvkJRZVFp871p0OM-q5sHILRX/view?usp=drive_link | NEW
DEF_KTS_HM_02 | KTS_HM_08 | The link should be secured | The link is not secured | 1. Open the page 2. Check the link | Major |  | https://drive.google.com/file/d/1Enm_QJntOQkWM4zY1w3-xCt2a0aNZCxp/view?usp=sharing | NEW
DEF_KTS_HM_03 | KTS_HM_11 | Explore more link should redirect into a page with more details | Explore more link does not redirects into a page with more details | 1. Open the page 2. Click on explore more | Critical |  | https://drive.google.com/file/d/15NZ7WCpK-B6Qm7pyueAmM-9VMzwA8h-j/view?usp=sharing | NEW
DEF_KTS_HM_04 | KTS_HM_12 | Read more about us link should redirect into a page with more info | Read more about us link does not redirect into a page with more info | 1. Open the page 2. Click on read more | Critical |  | https://drive.google.com/file/d/179U6oiAPVOYs334Dc5N8JLQ4ybLitN6b/view?usp=sharing | NEW
DEF_KTS_HM_05 | KTS_HM_13 | The read more link should be clickable | The read more link is not clickable | 1. Open the page 2. Click on read more | Critical |  | https://drive.google.com/file/d/1_pZUGsjeJkDLRSm4Z2vWGoxAZQ0n8Zfg/view?usp=sharing | NEW
DEF_KTS_HM_06 | KTS_HM_14 | The photos of the CEO should be provided | The photos of the CEO are not provided | 1. Open the page 2. Click for the photos of CEOs | Enhancement |  | https://drive.google.com/file/d/1S8S7sLCqxI3j4I96YAjs8q7zvvDGSRuK/view?usp=sharing | NEW
DEF_KTS_HM_07 | KTS_HM_15 | The view all link under latest news and blogs should redirect to the desired page | The view all link under latest news and blogs redirects to the desired page | 1. Open the page 2. Check for the latest news and blogs session 3. Click view all | Critical |  | https://drive.google.com/file/d/1G5of9V0Unzdy9CyU23uIjwaDqw4TfHqQ/view?usp=sharing | NEW
DEF_KTS_HM_08 | KTS_HM_16 | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | 1. Open the page 2. Click on the phone number | Major |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_HM_09 | KTS_HM_17 | The about kts under quick links should be working | The about kts under quick links is not working | 1. Open the page 2. Click on about kts under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_HM_10 | KTS_HM_18 | The services under quick links should be working | The services under quick links is not working | 1. Open the page 2. Click on services under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_HM_11 | KTS_HM_19 | The contact us under quick links should be working | The contact under quick links is not working | 1. Open the page 2. Click on contact under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_HM_12 | KTS_HM_20 | The blogs us under quick links should be working | The blogs under quick links is not working | 1. Open the page 2. Click on blogs under quick links | Major |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_HM_13 | KTS_HM_21 | Social media links should be present | Social media links are not present | 1. Open the page 2. Check for social media links | Enhancement |  | https://drive.google.com/file/d/1v91XlCIt8_gawh8Tv-FJV5qMfGY6oh_J/view?usp=sharing | NEW
DEF_KTS_HM_14 | KTS_HM_23 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter the name | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_HM_15 | KTS_HM_24 | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter the name | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_HM_16 | KTS_HM_26 | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_HM_17 | KTS_HM_27 | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter the email | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_HM_18 | KTS_HM_28 | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | 1. Open the page 2. Check for get in touch session 3. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_HM_19 | KTS_HM_31 | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | 1. Open the page 2. Check for get in touch session 3. Check whether the required field is marked as required | Enhancement |  | https://drive.google.com/file/d/1H4iO63voXLBDdNMkDL62ZVcML50Ws14Y/view?usp=sharing | NEW
DEF_KTS_HM_20 | KTS_HM_35 | The super markets link should redirect to the desired page | The super markets link redirect to the page which contain all services | 1. Open the page 2. Click the super markets | Major |  | https://drive.google.com/file/d/1T-_f0_aTVov9S4J__VDC8fsaI40zcE5I/view?usp=sharing | NEW
DEF_KTS_HM_21 | KTS_HM_36 | The car care link should redirect to the desired page | The car care link redirect to the page which contain all services | 1. Open the page 2. Click the car care | Major |  | https://drive.google.com/file/d/1T-_f0_aTVov9S4J__VDC8fsaI40zcE5I/view?usp=sharing | NEW
DEF_KTS_HM_22 | KTS_HM_37 | The truck spare parts link should redirect to the desired page | The truck spare parts linK redirect to the page which contain all services | 1. Open the page 2. Click the truck spare parts | Major |  | https://drive.google.com/file/d/1T-_f0_aTVov9S4J__VDC8fsaI40zcE5I/view?usp=sharing | NEW
DEF_KTS_HM_23 | KTS_HM_41 | The name field of enquiry form should not accept characters other than alphabets in enquiry form | The name field of enquiry form accept characters other than alphabets | 1. Open the page 2. Click on enquire now 3. Enter the name | Major |  | https://drive.google.com/file/d/1G-mJPevG5Ljmd9iLoUSuGnY6L_mENt-2/view?usp=sharing | NEW
DEF_KTS_HM_24 | KTS_HM_42 | There should be a limit for the number of characters in the name field in enquiry form | There is no limit for the number of characters in the name field in enquiry form | 1. Open the page 2. Click on enquire now 3. Enter the name | Minor |  | https://drive.google.com/file/d/1G-mJPevG5Ljmd9iLoUSuGnY6L_mENt-2/view?usp=sharing | NEW
DEF_KTS_HM_25 | KTS_HM_44 | An invalid email should not be accepted in enquiry form | An invalid email is accepted in enquiry form | 1. Open the page 2. Click on enquire now 3. Enter an invalid email | Major |  | https://drive.google.com/file/d/1G-mJPevG5Ljmd9iLoUSuGnY6L_mENt-2/view?usp=sharing | NEW
DEF_KTS_HM_26 | KTS_HM_45 | There should be a limit for the number of characters in the email field in enquiry form | There is no limit for the number of characters in the email field in enquiry form | 1. Open the page 2. Click on enquire now 3. Enter an email | Minor |  | https://drive.google.com/file/d/1G-mJPevG5Ljmd9iLoUSuGnY6L_mENt-2/view?usp=sharing | NEW
DEF_KTS_HM_27 | KTS_HM_46 | An error should be shown if an invalid email is entered in the enquiry form | An error is not shown if an invalid email is entered in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter an invalid email | Major |  | https://drive.google.com/file/d/1G-mJPevG5Ljmd9iLoUSuGnY6L_mENt-2/view?usp=sharing | NEW
DEF_KTS_HM_28 | KTS_HM_51 | The number field should not accept alphabets in the enquiry form | The number field accept alphabets in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter the number | Major |  | https://drive.google.com/file/d/1G-mJPevG5Ljmd9iLoUSuGnY6L_mENt-2/view?usp=sharing | NEW
DEF_KTS_HM_29 | KTS_HM_52 | There should be a limit of number of digits that can be entered in the number field | There is no limit of number of digits that can be entered in the number field | 1. Open the page 2. Click on enquire now 3. Enter the number | Minor |  | https://drive.google.com/file/d/1G-mJPevG5Ljmd9iLoUSuGnY6L_mENt-2/view?usp=sharing | NEW
DEF_KTS_HM_30 | KTS_HM_53 | The name field should not accept space as a text in the enquiry form | The field not accept space as a text in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter a space in name field 4. Click submit | Major |  | https://drive.google.com/file/d/11WilMSgfnx_Oj3cXFVyg47qW9lgRppaB/view?usp=sharing | NEW
DEF_KTS_HM_31 | KTS_HM_54 | The number field should not accept space as a text in the enquiry form | The number field accept space as a text in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter a space in number field 4. Click submit | Major |  | https://drive.google.com/file/d/11WilMSgfnx_Oj3cXFVyg47qW9lgRppaB/view?usp=sharing | NEW
DEF_KTS_HM_32 | KTS_HM_55 | The service field should not accept space as a text in the enquiry form | The service field accept space as a text in the enquiry form | 1. Open the page 2. Click on enquire now 3. Enter a space in service field 4. Click submit | Major |  | https://drive.google.com/file/d/11WilMSgfnx_Oj3cXFVyg47qW9lgRppaB/view?usp=sharing | NEW
DEF_KTS_HM_33 | KTS_HM_58 | The number field should accept number within the given format as per the SRS document | The number field accept number other than the given format as per the SRS document | 1. Open the page 2. Click on enquire now 3. Enter the number | Major |  | https://drive.google.com/file/d/1sIHR4OUMV9Vwuo6Qjbl6cWeFevt2faAb/view?usp=sharing | NEW
DEF_KTS_HM_34 | KTS_HM_61 | The name field should not accept space as a text in the get in touch form | The field not accept space as a text in the get in touch form | 1. Open the page 2. Go to get in touch 3. Enter a space in name field 4. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_HM_35 | KTS_HM_62 | The subject field should not accept space as a text in the get in touch form | The subject field accept space as a text in the get in touch form | 1. Open the page 2. Go to get in touch 3. Enter a space in subject field 4. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_HM_36 | KTS_HM_63 | The message field should not accept space as a text in the get in touch form | The message field accept space as a text in the get in touch form | 1. Open the page 2. Go to get in touch 3. Enter a space in message field 4. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_ABT_01 | KTS_ABT_04 | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | 1. Open the page 2. Click on about 3. Click on the phone number | Major |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_ABT_02 | KTS_ABT_05 | The about kts under quick links should be working | The about kts under quick links is not working | 1. Open the page 2. Click on about 3. Click on about kts under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_ABT_03 | KTS_ABT_06 | The services under quick links should be working | The services under quick links is not working | 1. Open the page 2. Click on about 3. Click on services under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_ABT_04 | KTS_ABT_07 | The contact us under quick links should be working | The contact under quick links is not working | 1. Open the page 2. Click on about 3. Click on contact under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_ABT_05 | KTS_ABT_08 | The blogs under quick links should be working | The blogs under quick links is not working | 1. Open the page 2. Click on about 3. Click on blogs under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_ABT_06 | KTS_ABT_10 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter the name | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_ABT_07 | KTS_ABT_11 | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter the name | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_ABT_08 | KTS_ABT_13 | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_ABT_09 | KTS_ABT_14 | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter the email | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_ABT_10 | KTS_ABT_15 | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_ABT_11 | KTS_ABT_18 | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | 1. Open the page 2. Click on about 3. Check for get in touch session 4. Check whether the required field is marked as required | Enhancement |  | https://drive.google.com/file/d/1H4iO63voXLBDdNMkDL62ZVcML50Ws14Y/view?usp=sharing | NEW
DEF_KTS_ABT_12 | KTS_ABT_23 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on about 3. Click on enquire now 4. Enter the number | Major |  | https://drive.google.com/file/d/1sIHR4OUMV9Vwuo6Qjbl6cWeFevt2faAb/view?usp=sharing | NEW
DEF_KTS_ABT_13 | KTS_ABT_24 | The name field should not accept space as a text in the get in touch form | The field not accept space as a text in the get in touch form | 1. Open the page 2. Click on about 3. Go to get in touch 4. Enter a space in name field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_ABT_14 | KTS_ABT_25 | The subject field should not accept space as a text in the get in touch form | The subject field accept space as a text in the get in touch form | 1. Open the page 2. Click on about 3. Go to get in touch 4. Enter a space in subject field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_ABT_15 | KTS_ABT_26 | The message field should not accept space as a text in the get in touch form | The message field accept space as a text in the get in touch form | 1. Open the page 2. Click on about 3. Go to get in touch 4. Enter a space in message field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_SRV_01 | KTS_SRV_04 | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | 1. Open the page 2. Click on services 3. Click on the phone number | Major |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_SRV_02 | KTS_SRV_05 | The about kts under quick links should be working | The about kts under quick links is not working | 1. Open the page 2. Click on services 3. Click on about kts under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_SRV_03 | KTS_SRV_06 | The services under quick links should be working | The services under quick links is not working | 1. Open the page 2. Click on services 3. Click on services under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_SRV_04 | KTS_SRV_07 | The contact us under quick links should be working | The contact under quick links is not working | 1. Open the page 2. Click on services 3. Click on contact under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_SRV_05 | KTS_SRV_08 | The blogs us under quick links should be working | The blogs under quick links is not working | 1. Open the page 2. Click on services 3. Click on blogs under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_SRV_06 | KTS_SRV_10 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter the name | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_SRV_07 | KTS_SRV_11 | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter the name | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_SRV_08 | KTS_SRV_13 | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_SRV_09 | KTS_SRV_14 | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter the email | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_SRV_10 | KTS_SRV_15 | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_SRV_11 | KTS_SRV_18 | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | 1. Open the page 2. Click on services 3. Check for get in touch session 4. Check whether the required field is marked as required | Enhancement |  | https://drive.google.com/file/d/1H4iO63voXLBDdNMkDL62ZVcML50Ws14Y/view?usp=sharing | NEW
DEF_KTS_SRV_12 | KTS_SRV_23 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on services 3. Click on enquire now 4. Enter the number | Major |  | https://drive.google.com/file/d/1sIHR4OUMV9Vwuo6Qjbl6cWeFevt2faAb/view?usp=sharing | NEW
DEF_KTS_SRV_13 | KTS_SRV_24 | The name field should not accept space as a text in the get in touch form | The field not accept space as a text in the get in touch form | 1. Open the page 2. Click on services 3. Go to get in touch 4. Enter a space in name field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_SRV_14 | KTS_SRV_25 | The subject field should not accept space as a text in the get in touch form | The subject field accept space as a text in the get in touch form | 1. Open the page 2. Click on services 3. Go to get in touch 4. Enter a space in subject field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_SRV_15 | KTS_SRV_26 | The message field should not accept space as a text in the get in touch form | The message field accept space as a text in the get in touch form | 1. Open the page 2. Click on services 3. Go to get in touch 4. Enter a space in message field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_BLG_01 | KTS_BLG_03 | The text should be readable and understandable | The text is not readable and understandable | 1. Open the page 2. Click on blogs | Trivial |  | https://drive.google.com/file/d/1QGxPw7-9SwMhe28G8LmBOsyK6wy5AKKY/view?usp=sharing | NEW
DEF_KTS_BLG_02 | KTS_BLG_04 | When clicked on phone number, it should show a pop-up | When clicked on phone number, it does not show a pop-up | 1. Open the page 2. Click on blogs 3. Click on the phone number | Major |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_BLG_03 | KTS_BLG_05 | The about kts under quick links should be working | The about kts under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on about kts under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_BLG_04 | KTS_BLG_06 | The services under quick links should be working | The services under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on services under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_BLG_05 | KTS_BLG_07 | The contact us under quick links should be working | The contact under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on contact under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_BLG_06 | KTS_BLG_08 | The blogs under quick links should be working | The blogs under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on blogs under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_BLG_07 | KTS_BLG_10 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the name | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_BLG_08 | KTS_BLG_11 | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the name | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_BLG_09 | KTS_BLG_13 | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_BLG_10 | KTS_BLG_14 | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the email | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_BLG_11 | KTS_BLG_15 | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_BLG_12 | KTS_BLG_18 | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Check whether the required field is marked as required | Enhancement |  | https://drive.google.com/file/d/1H4iO63voXLBDdNMkDL62ZVcML50Ws14Y/view?usp=sharing | NEW
DEF_KTS_BLG_13 | KTS_BLG_23 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on blogs 3. Click on enquire now 4. Enter the number | Major |  | https://drive.google.com/file/d/1sIHR4OUMV9Vwuo6Qjbl6cWeFevt2faAb/view?usp=sharing | NEW
DEF_KTS_BLG_14 | KTS_BLG_24 | The name field should not accept space as a text in the get in touch form | The field not accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in name field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_BLG_15 | KTS_BLG_25 | The subject field should not accept space as a text in the get in touch form | The subject field accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in subject field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_BLG_16 | KTS_BLG_26 | The message field should not accept space as a text in the get in touch form | The message field accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in message field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_CNT_01 | KTS_CNT_03 | The text should be readable and understandable | The text is not readable and understandable | 1. Open the page 2. Click on blogs | Trivial |  | https://drive.google.com/file/d/1QGxPw7-9SwMhe28G8LmBOsyK6wy5AKKY/view?usp=sharing | NEW
DEF_KTS_CNT_02 | KTS_CNT_05 | The about kts under quick links should be working | The about kts under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on about kts under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_CNT_03 | KTS_CNT_06 | The services under quick links should be working | The services under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on services under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_CNT_04 | KTS_CNT_07 | The contact us under quick links should be working | The contact under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on contact under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_CNT_05 | KTS_CNT_08 | The blogs under quick links should be working | The blogs under quick links is not working | 1. Open the page 2. Click on blogs 3. Click on blogs under quick links | Critical |  | https://drive.google.com/file/d/1Ox2tbr2wKHrj4578Q70PZ5wuGJIPDHg-/view?usp=sharing | NEW
DEF_KTS_CNT_06 | KTS_CNT_10 | The name field should not accept characters other than alphabets in the get in touch | The name field accept characters other than alphabets in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the name | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_CNT_07 | KTS_CNT_11 | There should be a limit for the number of characters in the name field in the get in touch | There is no limit for the number of characters in the name field in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the name | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_CNT_08 | KTS_CNT_13 | An invalid email should not be accepted in the get in touch | An invalid email is accepted in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_CNT_09 | KTS_CNT_14 | There should be a limit for the number of characters in the email field in the get in touch | There is no limit for the number of characters in the email field in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter the email | Minor |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_CNT_10 | KTS_CNT_15 | An error should be shown if an invalid email is entered in the get in touch | An error is not shown if an invalid email is entered in the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Enter an invalid email | Major |  | https://drive.google.com/file/d/1btRCZcPOFrMkyM9sbQF4D6mHgbWdklhZ/view?usp=sharing | NEW
DEF_KTS_CNT_11 | KTS_CNT_18 | The fields that are required should be marked as required the get in touch | The fields that are required are not marked as required the get in touch | 1. Open the page 2. Click on blogs 3. Check for get in touch session 4. Check whether the required field is marked as required | Enhancement |  | https://drive.google.com/file/d/1H4iO63voXLBDdNMkDL62ZVcML50Ws14Y/view?usp=sharing | NEW
DEF_KTS_CNT_12 | KTS_CNT_23 | The number field should accept number within the given format as per the SRS document | The number field accept number within the given format as per the SRS document | 1. Open the page 2. Click on blogs 3. Click on enquire now 4. Enter the number | Major |  | https://drive.google.com/file/d/1sIHR4OUMV9Vwuo6Qjbl6cWeFevt2faAb/view?usp=sharing | NEW
DEF_KTS_CNT_13 | KTS_CNT_24 | The name field should not accept space as a text in the get in touch form | The field not accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in name field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_CNT_14 | KTS_CNT_25 | The subject field should not accept space as a text in the get in touch form | The subject field accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in subject field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_CNT_15 | KTS_CNT_26 | The message field should not accept space as a text in the get in touch form | The message field accept space as a text in the get in touch form | 1. Open the page 2. Click on blogs 3. Go to get in touch 4. Enter a space in message field 5. Click send message | Major |  | https://drive.google.com/file/d/1NDK3fblbNrE6T0eCAv0Bnmk42XeYJ0nD/view?usp=sharing | NEW
DEF_KTS_CNT_16 | KTS_CNT_40 | The given location should be correct | The given location is not correct | 1. Open the page 2. Click on contact 3. Click on the map | Major |  | https://drive.google.com/file/d/1eeBSJAOegegGlo1eraIwBzuz6zPygpLF/view?usp=sharing | NEW

## DEFECT DISTRIBUTION
KTS PVT
MODULE NAME | DEFECT DISTRIBUTION
HOME | 36
ABOUT | 15
SERVICES | 15
BLOGS | 16
CONTACT | 16

## TEST REPORT
KTS PVT
SL NO. | MODULE NAME | TEST CASE PASSED | TEST CASE FAILED | TOTAL TEST CASE
1 | HOME | 29 | 36 | 65
2 | ABOUT | 12 | 15 | 27
3 | SERVICES | 25 | 15 | 40
4 | BLOGS | 14 | 16 | 30
5 | CONTACT | 29 | 16 | 45